## Sheet1
Sean and Bella Irwin | Cutting to be done outside.
Terrace Bay, ON
Sept. 2008 |  |  |  | Phil |  | Min
Estimate |  |  |  | 2
sell |  |  |  | 0.5
Pick up material 4x+ | HD/Design,Western,stain/paint |  |  | 2
Pack/set-up |  |  |  | 2
Travel time |  |  |  | 4 |  | 4
Re stain walls and finish with 1 coat premium polyurethane. | [5 empty] | 8
scaffolding-set-up/teardown-crown and stain/finish |  |  |  | 2 |  | 1
Install cove for hardwood under hutch cabinet. |  |  |  | 0.5
paint and install 30’ thick paint grade crown and touch-up. |  |  |  | 6 |  | 2
Install 1- 1-1/2” x 8’ paint grade corner cap |  |  |  | 0.5 |  | 0.5
Install baseboard under hardwood by TV room |  |  |  | 1 |  | 0
13-1/4” between existing black iron pipe = 2 more balusters
Add 2 x 11 = 22 pcs. x 36” BIP
22 - 1” black iron pipe x 36” balusters cut and trim on angle |  |  |  | 3 |  | 1
drill holes 3/4" up from bottom to attach to treads |  |  |  | 2
install 22 - 1” black iron pipe x 36” balusters |  |  |  | 8
prime and paint balusters with 2 coats finish paint/touchup | [5 empty] | 8
mill 11 spiral stair treads in shop
plane 5-1 x 8 x 8 oak |  |  |  | 1
joint,laminate 22 pieces/remove from clamps |  |  |  | 5
cut out 11 treads to pattern-concave inside/convex outside |  |  |  | 4
mill/install front nosing x11 |  |  |  | 2
mill/install side nosing x11 |  |  |  | 2
roundover |  |  |  | 1
margin |  |  |  | 1
sand curves and flats | [5 empty] | 2
finish to match existing hardwood and touchup | [5 empty] | 8
remove existing treads and carpet | [5 empty] | 2
dispose | [5 empty] | 0.5
install treads with screws from below |  | 11 | 0.5 | 5.5
margin |  |  |  | 2 |  | 1
16’ spiral stair rail-16” x 11 pcs. 176”
plough groove ¾” deep for BIP existing = 5/16” |  |  |  | 2
cut angle/pattern |  |  |  | 1
cut and fit 11 pieces-problem at wall |  |  |  | 8
cut and fit fillet |  |  |  | 1
sand | [5 empty] | 1
finish in place | [5 empty] | 3
extra margin |  |  |  | 2 |  | 2
handrail on landing
1 post 34” 1/2 post at wall
1/2 post 41” 1 post
Install 2 posts and 2- 1/2 posts |  |  |  | 5
Install 2 rail-3' and 4' |  |  |  | 2
install 22 balusters |  |  |  | 4
clean |  |  |  | 1 |  | 1
margin |  |  |  | 1 |  | 1
teardown |  |  |  | 1
pack |  |  |  | 1
Finishing
sand | [5 empty] | 1
varnish x 2 | [5 empty] | 3
touch-up | [5 empty] | 1
|  |  |  | 86 |  | 51
total Phil | 86 | 50 | 4300
total Min | 51 | 30 | 1530
sub-total labour |  |  | 5830 |  |  | 5830
50% mark-up on labour | 50% |  | 2915 |  | 65% | 3789.5
total labour |  |  | 8745 |  |  | 9619.5
total material |  |  | 2316.0816 |  |  | 2316.0816
total |  |  | 11061.0816 |  |  | 11935.5816
|  |  | 10820 |  |  | 11500
material
handrail |  | elias | design
1 post 34” 1/2 post at wall
1/2 post 41” 1 post
2 posts | 2 | 46 | 80.75 | 161.5
2 1/2 posts | 2 | 21 | 52.25 | 104.5
8' rail | 1 | 30 | 72 | 72
36" balusters | 22 | 7.37 | 15.56 | 342.32
suretites | 2 |  | 16 | 32
shipping |  |  |  | 75
thick p.g. crown 8+/6/6/8 | 30 |  | 4 | 120 | check price
3/4" oak cove | 10 |  | 2 | 20 | "
1-1/2: pg corner | 8 |  | 1.5 | 12 | "
1" x 21' BIP | 4 |  | 46 | 184 | Western
8- 1" x 8 x 8 oak= 43 bd.' | 43 | 5 |  | 215 | check price
grinding wheels |  |  |  | 15
mileage | 300 |  | 0.5 | 150
stain |  |  |  | 25
maxithane, etc. |  |  |  | 75
misc. |  |  |  | 75
subtotal material |  |  |  | 1678.32
13% tax | 13% |  |  | 218.1816
25% markup on subtotal e99 | 25% |  |  | 419.58
total material |  |  |  | 2316.0816
11 treads 2 tread blanks = 3- 1 x 8 x 30
6 blanks =18 x 1 x 8 x30 = 8- 1 x 8 x 8’
Cut top on angle with skilsaw/angle grinder and jig
drill bottom of baluster for attachment to new tread (nosing on ends to allow for bolting in tight spots )
sub-total material |  |  | 4372.5
30% mark-up on material |  |  | 13117.5
total material |  |  | 1725
total |  |  | 517.5
2242.5